## Sheet1
Big Data Analytics Project Task List - Summer 2019
Project Name: | What’s the next hot area in Computer Science field?
Team Members: | 1) Yijun Tian
2) Rui Jin
3) Fan Xie
4)
Task | Who | Start Date | End Date | Comments
Data Planning Stage
Identify data sources | All | 01/July | 15/July
Plan where data will reside | All | 01/July | 15/July | •How much total data will be stored at any given time? 10GB
•Will the data fit in your Quickstart VM's HDFS, or do you need to use Dumbo? or the Cloud? Dumbo
Data Source 1 Processing
Write code to ingest data source 1 | Fan | 16/July | 26/July | •In this step, you'll read the data from the source and write it or copy it into HDFS
Write code to profile data source 1 | Fan | 16/July | 26/July | •This is to characterize the data and the range of values in each column
•You might notice unexpected values in a column - you may decide to normalize the values (e.g. Street vs. St. vs. street) in the ETL stage
•Find min, max, and averages
•Find min and max length of text fields
Write code to clean/format (ETL) data source 1 | Fan | 16/July | 26/July
Data Source 2 Processing
Write code to ingest data source 2 | Rui | 16/July | 26/July | •In this step, you'll read the data from the source and write it or copy it into HDFS
Write code to profile data source 2 | Rui | 16/July | 26/July | •This is to characterize the data and the range of values in each column
•You might notice unexpected values in a column - you may decide to normalize the values (e.g. Street vs. St. vs. street) in the ETL stage
•Find min, max, and averages
•Find min and max length of text fields
Write code to clean/format (ETL) data source 2 | Rui | 16/July | 26/July
Data Source 3 Processing
Write code to ingest data source 3 | Yijun | 16/July | 26/July | •In this step, you'll read the data from the source and write it or copy it into HDFS
Write code to profile data source 3 | Yijun | 16/July | 26/July | •This is to characterize the data and the range of values in each column
•You might notice unexpected values in a column - you may decide to normalize the values (e.g. Street vs. St. vs. street) in the ETL stage
•Find min, max, and averages
•Find min and max length of text fields
Write code to clean/format (ETL) data source 3 | Yijun | 16/July | 26/July
Develop, Test, and Refine the Analytic
Design the analytic(s) | All | 27/July | 06/Aug
Code the analytic(s) | All | 27/July | 06/Aug
Test the analytic(s) | All | 27/July | 06/Aug
Analyze results of analytic(s) | All | 27/July | 06/Aug | •Are the results what you expected?
| All | 27/July | 06/Aug | •Do you need to adjust the analytic(s)?
Iterate on the analytic | All | 27/July | 06/Aug | •To improve results, and/or to better understand results
Final analytic code due | All | -
Copyright Suzanne McIntosh 2013-2019